Short Sketch to assess suitability to the Exist funding programs

1. Project Title

PhageMatch – AI-Driven Precision Phage Therapy Platform

2. Team/ Applicants

Abdullah Hanif (Saarland University, Bioinformatics), Dr. Oliver Köhn (AI/Data Science), and Zahra Asgharzada (Microbiology). Our interdisciplinary team combines expertise in machine learning, high-performance computing, and microbiology to revolutionize phage therapy.

3. Idea and Innovation

PhageMatch is a next-generation AI platform that predicts optimal bacteriophage-host interactions using multi-omics data integration. Unlike existing alignment-based or single-feature models (PhARIS, HostPhinder), PhageMatch employs Graph Neural Networks (GNNs) and Self-Supervised Learning (SSL) to capture complex phage-bacteria relationships, achieving higher accuracy and generalizability. Our innovation lies in dynamic data augmentation, hybrid multi-modal models, and real-time analysis, addressing critical gaps in current phage therapy methods.

4. Market and Target Group

Target markets include hospitals combating multidrug-resistant infections, agricultural sectors managing bacterial outbreaks, and phage therapy research labs. The global antibiotic resistance crisis (1M+ deaths/year) underscores an urgent need, with phage therapy projected to grow at 4.5% CAGR. Competitors lack AI-driven multi-omics integration, giving PhageMatch a unique edge.

5. Implementation Plan

- Phase 1 (0–3 months): Secure data partnerships (Phagen Biotechnology Lab and Eliava Institute) and build HPC infrastructure.

- Phase 2 (4–9 months): Develop AI models (GNNs, SSL) and validate with lab data.

- Phase 3 (10–12 months): Pilot testing in clinical/lab settings (University Hospital Frankfurt collaboration).

- Phase 4 (12+ months): Commercialize SaaS platform and pursue regulatory approvals.

6. Resources and Funding 
Requested funds will cover:

- AI/Cloud Infrastructure (AWS/GCP GPU clusters, secure storage);

- Data Licensing (Phagen Biotechnology Lab’s proprietary datasets);

- Lab Validation (in vitro assays via University Hospital Frankfurt collaboration);

- Team Salaries (full-time AI, microbiology, and bioinformatics roles);

- Contingency (regulatory/validation surprises).

7. Contact Person (max. 300 characters / 2-3 sentences)

Abdullah Hanif a master’s student in Bioinformatics at Saarland University.

Email: abha00004@stud.uni-saarland.de , Phone: +49 152 12581892